## Risk log
Risk Register
Project name: Sound Visualisation Project
Project Members: Shane Monck, Caleb Cheng, Kese Gasbarri, Darby Edwards, Aditi Malu
ID | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens.
1 | Project proposal and deliverable definition is incomplete/not well defined. | Low | High | High | Project Sponsor | Project purpose is re-analysed and discussed with the team with inputs from all sponsor members | Discuss with team about important aspects of projects to be fulfilled. Request high risk requirments to be cut down and removed.
2 | Scope not well defined | Low | High | High | Team | Effective communication with client to make sure scope isnt missing details, or unnecessary features are not added which would lengthen the project lead time. | Share the plan and go through upcoming tasks with client as soon as possible.
3 | Lack of communication with client causing lack of clarity and confusion | Medium | Medium | Medium | Project Manager | Effective and regular communication with client. Updating client regularly about the project. Ensure that we have detailed and up-to-date documentation on all aspects of project. | Correct misunderstandings immediately in project with client. Clarify areas that are not clear swiftly using assistance from Client
4 | Scope creep/Risk in Scope Variation | Medium | High | High | Team | Keep documentation as up to date as possible to adapt to new changes if needed. Additional feature requests must be evaluated in terms of likely project impact, and decisions then need to be made in terms of whether to include or not include the new feature requests in the current phase. | Documentation of every new feature is necessary no matter how many changes. Authorisation from Client before any new changes are implemented.
5 | Unresolved project detail conflicts | Low | Medium | Medium | Team | Hold regular meetings apart from formal meetings to ensure project details are discussed with every member. Give reviews of project plan to client in case of conflicts. | To resolve issues, discuss with team and client immediately as soon as conflict is identified.
6 | Delay on early stage deliverables resulting in late submission. | Medium | High | High | Team | Ensure following the timetable as listed on CITS3200 page. Schedule other important requirements to ensure everyone is following the schedule. | Collaborate with team members to help recover from slow progress. Ensure that everyone is aware about immediate deadlines.
7 | User experience | Low | Medium | Medium | Team | Make sure that website is user friendly and easy to use. Simple features will create the perfect user experience | Simplify features and discuss with client what parts are difficult to use to immediately change features
8 | Lack of Scalability and Integration to Clients Software | Low | Low | Low | Team | Since team isn't aware of exact system used by client, it is difficult to know if integration will be completely perfect. Make sure client understands this. | Help client in changing features to ensure seamless integration and scalabilty to their systems.
9 | Poor software quality | Medium | High | Medium | Team | Initiate review and testing early on; retest after fixes or changes.Plan for adequate time for testing and bug fixing. Make sure code is secure and ensures good speed performance. | Analyze the causes of errors with the objective of implementing process improvements. Test and change parts as required.
10 | Poor team dynamics | Medium | Medium | Medium | Project Manager | Ensure team cohesion through proactive communication. Implement processes to escalate conflict resolution to auditor or unit coordinator t if needed. | Correct misunderstandings and investigate reasons for conflict then provide feedback to each other on possible corrective measures.

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low